## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | CT Project | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Futurewei Technologies, Inc. | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Kirk Kim |  | Project Start Date: |  | 2020-06-01
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | June | [34 empty] | July
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-06-01 to 2020-07-26
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Marketing Study & Product Features
| Existing Solution and App Analysis | Low Risk | Jack | 100% | 2020-06-02 | 8
| Define Features and use case scenarios | Low Risk | Jack | 100% | 2020-06-04 | 13
| Propose general system architecture | Low Risk | Jack | 100% | 2020-06-02 | 3
| Identify HMS Kits and Capabilities | Low Risk | Jack | 60% | 2020-06-02 | 15
| Google/apple CT doc Analysis | Low Risk | Jack | 100% | 2020-06-05 | 7
| Contact Shield doc analysis | Low Risk | Jack, Jenny | 100% | 2020-06-11 | 1
| Experiment and define solution | Low Risk | Jack | 100% | 2020-06-08 | 5
| Show basic UX flow | Low Risk | Jenny | 100% | 2020-06-10 | 2
| Analyzed UI/UX design | Low Risk | Jenny | 100% | 2020-06-08 | 5
| Presentation | Milestone | Jack, Jenny | 100% | 2020-06-12 | 1 | bar: F
Research
| Germany's approach research | Low Risk | Jack | 100% | 2020-06-15 | 1
| Google/Apple API issue research | Low Risk | Jack | 100% | 2020-06-16 | 1
| Huawei CS kit document and API research | Low Risk | Jack | 100% | 2020-06-17 | 1
| Google server code and document research | Low Risk | Jack | 100% | 2020-06-18 | 1
| Dashboard research and plan | Low Risk | Jenny | 100% | 2020-06-24 | 3 | bar: W to T
| Germany's approach on verification server | Low Risk | Jack | 100% | 2020-06-29 | 2 | bar: W to T
Application Development
| Detailed Use Cases and Scenario Design | Low Risk | Jack, Jenny | 80% | 2020-06-15 | 4
| System Design: apk, server, data | Low Risk | Jack, Jenny | 80% | 2020-06-18 | 10
| APP UI/UX Design | Low Risk | Jack, Jenny | 80% | 2020-06-15 | 25
| APK design/Coding/Testing | Low Risk | Jack, Jenny | 80% | 2020-06-15 | 25
| Server Design/Coding/Testing | Med Risk | Jack, Jenny | 80% | 2020-06-15 | 25
| End to End testing | Med Risk | Jack, Jenny | 90% | 2020-06-15 | 25
| Dashboard Design and Implementation | Low Risk | Jenny | 90% | 2020-06-29 | 14
| Huawei Push Kit implementation | Low Risk | Jenny | 100% | 2020-07-07 | 14
| Tried Google/Apple API | Low Risk | Jack | 100% | 2020-06-18 | 1
| Tried Huawei CS API | Low Risk | Jack | 100% | 2020-06-18 | 1
| Implemented UX | Low Risk | Jack | 100% | 2020-06-20 | 28
| Implemented server side code for verification center | Low Risk | Jack | 100% | 2020-07-01 | 7
| Implemented the refined Uploading PK process | Low Risk | Jack | 90% | 2020-07-05 | 4
| Implmented a console for testing center | Low Risk | Jack | 100% | 2020-07-09 | 6
| Implemented a console for verification authority | Low Risk | Jack | 100% | 2020-07-09 | 6
| Implemented the error handling part on server and client | Low Risk | Jack | 100% | 2020-07-13 | 5
| Switch to the latest CS kit (4.1.0.302) | Low Risk | Jack | 100% | 2020-07-13 | 10
| Analyzed using SonarQube and re-structured the code | Low Risk | Jack | 100% | 2020-07-30 | 3
| Transfer dashboard to company | Low Risk | Jenny | 60% | 2020-08-07 | 2
| Transfer code to company | Low Risk | Jack | 100% | 2020-08-03 | 2
| Implement data collecting functions for the deployment | Low Risk | Jack | 100% | 2020-08-12 | 2
| Demo App Release | Milestone | Jack, Jenny | 0% | 2020-08-15 | 1
Deployment
| Create Deployment Document | Low Risk | Jenny | 70% | 2020-08-01 | 14
| Run through Deployment cases | Low Risk | Jack, Jenny | 0% | 2020-08-10 | 2
User Testing and Feeback
| User Testing and Feeback | Low Risk | Jack, Jenny | 0% | 2020-08-18 | 4
| Gathering test data | Med Risk | Jack, Jenny | 0% | 2020-08-18 | 14
| Analysis | Low Risk | Jack, Jenny | 0% | 2020-08-25 | 6
This is an empty row | Presentation | Milestone | Jack, Jenny | 0% | 2020-08-28 | 19
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | Training
| HMS Core and Capability Overview | Low Risk | Jack | 100% | 2020-06-02 | 2
| Watch Videos and Code Lab | Low Risk | Jack | 30% | 2020-06-02 | 10
| HMS Core and Capability Overview | Low Risk | Jenny | 100% | 2020-06-08 | 2
| Watch Videos and Code Lab | Low Risk | Jenny | 50% | 2020-06-08 | 10 | bar: T
| Publish demo App to AG | Milestone | Jack, Jenny | 0% | 2020-06-30 | 1
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.